## Test summary report
Tester | Hải Đăng, Quang Hiển, Sĩ Đức, Khắc Tấn, Văn Hiếu
Date | 2023-01-11
Number of functions be tested | 5
Number of test cases | 25
Feature's ID | Feature's Name | Number of test cases | Number of passed test cases | Number of failed test cases of a function
UC01 | Login by Email | 8 | 6 | 2
UC02 | Login by Google | 2 | 2 | 0
UC03 | Forgot Password? | 4 | 4 | 0
UC04 | Sign up by email | 9 | 9 | 0
UC05 | Swipe left - Swipe right (Dislike and like) | 2 | 2 | 0

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Case ID | Severity | Reported By | Date Reported | Status | Comment
B001 | Notice that the account is temporarily unable to log in instead of the wrong login when entering the wrong Email. | The system does not allow the account to send a login request because the account has failed to log in many times near each other. | UI01 | UC02 | Low | Hải Đăng | 2023-01-11 | Closed
B002 | Notice that the account is temporarily unable to log in instead of the wrong login when entering the wrong Password. | The system does not allow the account to send a login request because the account has failed to log in many times near each other. | UI01 | UC03 | Low | Hải Đăng | 2023-01-11 | Closed
Note on D1: Function ID of the function where the defect is found
Note on F1: High, Medium, or Low
Note on G1: Name of the tester who reports the defect
Note on I1: Open or Closed